## Sheet1
STT | MSSV | Họ tên | Ngày (yyyy-mm-dd) | Task | Thời gian (hours)
1 | 18125087 | Lê Tuấn Khanh | 2019-03-01 | implement login function: for admins, students and lecturers | 3
2 | 18125087 | Lê Tuấn Khanh | 2019-03-04 | implement password changing function | 2
3 | 18125087 | Lê Tuấn Khanh | 2019-03-08 | implement student importing function: read file csv and convert to txt file | 1
4 | 18125087 | Lê Tuấn Khanh | 2019-03-10 | implement logout function | 0.5
5 | 18125087 | Lê Tuấn Khanh | 2019-03-14 | implement class list viewing function | 0.5
6 | 18125087 | Lê Tuấn Khanh | 2019-03-14 | implement student-in-a-class viewing function | 0.5
7 | 18125087 | Lê Tuấn Khanh | 2019-03-15 | implement function to import courses from a semester | 1
8 | 18125087 | Lê Tuấn Khanh | 2019-03-16 | implement function to search and view scoreboard of a list | 2
9 | 18125087 | Lê Tuấn Khanh | 2019-03-17 | implement function to export a scoreboard to a csv file | 0.5
10 | 18125087 | Lê Tuấn Khanh | 2019-03-18 | implement function to view list of students of a course | 1.5
11 | 18125087 | Lê Tuấn Khanh | 2019-03-20 | implement function to view a scoreboard of a course | 0.5
12 | 18125087 | Lê Tuấn Khanh | 2019-03-22 | implement function to view a schedule of a class | 1
13 | 18125087 | Lê Tuấn Khanh | 2019-03-25 | implement function to view scores of a specific student | 1
14 | 18125087 | Lê Tuấn Khanh | 2019-04-04 | Apply color decorations to the program | 1.5
15 | 18125087 | Lê Tuấn Khanh | 2019-04-05 | apply password masking feature | 1
16 | 18125087 | Lê Tuấn Khanh | 2019-04-06 | create and get data for source files (courses, login,....) | 3
17 | 18125087 | Lê Tuấn Khanh | 2019-01-03 | implement student menu function | 2
18 | 18125090 | Ngô Minh Khôi | 2019-03-01 | apply keyboard control | 1.5
19 | 18125090 | Ngô Minh Khôi | 2019-03-04 | implement function to view profile info | 0.5
20 | 18125090 | Ngô Minh Khôi | 2019-03-08 | implement function to add a student to a class | 1
21 | 18125090 | Ngô Minh Khôi | 2019-03-10 | implement function to edit a student information | 1
22 | 18125090 | Ngô Minh Khôi | 2019-03-14 | implement function to remove a student from a class | 1.5
23 | 18125090 | Ngô Minh Khôi | 2019-03-14 | implement function to change a student from class A to B | 2
24 | 18125090 | Ngô Minh Khôi | 2019-03-15 | implement function to create / update / delete / view academic years (2018-2019), and semesters (Fall) | 2
25 | 18125090 | Ngô Minh Khôi | 2019-03-16 | implement function to add a course | 0.5
26 | 18125090 | Ngô Minh Khôi | 2019-03-17 | implement function to remove a course | 0.5
27 | 18125090 | Ngô Minh Khôi | 2019-03-18 | implement function to edit a course | 0.5
28 | 18125090 | Ngô Minh Khôi | 2019-03-20 | implement function to remove a student from a course | 0.5
29 | 18125090 | Ngô Minh Khôi | 2019-03-22 | implement function to add a student to a course | 1
30 | 18125090 | Ngô Minh Khôi | 2019-03-25 | implement function to view list of courses in the current semester | 0.5
31 | 18125090 | Ngô Minh Khôi | 2019-04-04 | implement function to view list of students of a course | 0.5
32 | 18125090 | Ngô Minh Khôi | 2019-04-05 | implement function to create / update / delete / view all lecturers | 2
33 | 18125090 | Ngô Minh Khôi | 2019-04-06 | implement function to view list of courses in the current semester | 0.5
34 | 18125090 | Ngô Minh Khôi | 2019-04-06 | implement function to view list of students of a course | 1
35 | 18125090 | Ngô Minh Khôi | 2019-04-06 | implement function to import scoreboard of a course (midterm, final, bonus, average) from a csv file | 1.5
36 | 18125090 | Ngô Minh Khôi | 2019-04-07 | implement function to edit grade of a student | 1
37 | 18125090 | Ngô Minh Khôi | 2019-04-07 | update function to view list of student of a course | 0.5
38 | 18125090 | Ngô Minh Khôi | 2019-04-08 | decorate login menu | 0.5
39 | 18125090 | Ngô Minh Khôi | 2019-04-09 | implement admin menu function | 1
40 | 18125090 | Ngô Minh Khôi | 2019-04-09 | implement lecturer menu function | 1.5
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200